NEON EVENTS ELEMENTS

Odoo Build Programme

Phase 7 — Staging Proposal

Training System — Sub-Phase Breakdown

Working document — 20 May 2026

# Why staging

Robin's Phase 7 Open Questions answers (locked 20 May 2026) chose the maximalist option across most groups: org-wide user coverage (A2=B), all four certification categories including soft skills (B1=D), formal approval workflow for external training (E2=A), Knowledge Base as core scope (F1=A), and layered three-tier event_job assignment gating (G2=D). The result: estimated 19–24 milestones across the full phase — roughly twice the scope of Phase 6.

Building this as a single linear phase means Robin sees no production value until ~8 weeks of build complete. Sub-phase staging means each major capability ships independently as it's ready. Phase 7a (the foundation) delivers operational value in ~3 weeks instead of 8.

This proposal breaks Phase 7 into four logical sub-phases. Each ships as a tagged production release, gets walkthrough acceptance, then the next sub-phase begins design. Master plan numbering stays at 12 phases — sub-phases are tracked internally.

# The four sub-phases at a glance

| Sub-phase | Focus | Milestones | Build time |
| --- | --- | --- | --- |
| 7a — Core | Certifications, competency, audit, event_job gating | ~10–12 | ~3 weeks |
| 7b — Onboarding & Self-service | Curriculum, probation, mentor, crew portal | ~4–5 | ~1–1.5 weeks |
| 7c — External Training | Vendor + course + booking + approval workflow | ~3–4 | ~1 week |
| 7d — Custom KB | SOP repository — articles, search, permissions, versioning | ~5–7 | ~3–4 weeks |
| Total | All Phase 7 | ~22–28 | ~8–10 weeks |

Estimates reflect Phase 6's actual cadence (10–12 milestones over ~3 weeks for a similar scope). Phase 7a is sized to match Phase 6 exactly so the rhythm is familiar.

# Phase 7a — Core (foundation)

First sub-phase. Anchors everything else. Ships before 7b/7c/7d are designed in detail — they sketch as we build.

| Field | Detail |
| --- | --- |
| What it includes | Certification taxonomy (Equipment + Role Tier + Safety + Soft Skills). Per-person certification records with attachments and admin verification. Per-category skill levels (binary or tiered). Mixed sign-off authority (Lead Tech / OD-MD / external trainer). Expiry tracking with 90/30/7 day reminders. Cross-competency model ('Bob doesn't have MA3 cert but ran it successfully on May event'). Event_job assignment integration with layered three-tier gating (informational at assignment / warning at quote-acceptance / blocking at event-start, all with override-reason logging). |
| What it excludes | Onboarding curriculum (7b). Crew self-service portal (7b). External training booking (7c). KB / SOPs (7d). |
| Module name | neon_training |
| Dependencies | neon_jobs (event_job), neon_crm_extensions, neon_finance (read-only for audit pattern reuse). |
| Value at completion | Ranganai can record all crew certifications. Sales reps see qualification status when assigning crew to event_job roles. Event-start gating prevents unqualified crew on confirmed jobs. Reminders flow via WhatsApp + email + in-app TODO. |
| Milestones (est.) | 10–12 |
| Build time (est.) | ~3 weeks at Phase 6 cadence |

Milestone outline for 7a (subject to schema sketch confirmation):

- M1 — Certification category + type models, admin views, audit-trail setup

- M2 — Certification record per person, file attachments, admin verification workflow

- M3 — Per-category configurable skill levels (binary / 3-tier / per-category configurable)

- M4 — Expiry tracking, computed states (active / expired / pending-verification / suspended), cron for state transitions

- M5 — Notification dispatch (90 / 30 / 7 day reminders via WhatsApp + email + TODO)

- M6 — Cross-competency model ("successfully demonstrated on event X" workflow)

- M7 — Sign-off authority workflow (Lead Tech / OD-MD / external trainer routing)

- M8 — Event_job role line extensions — required_certifications field, computed inference from role + equipment

- M9 — Layered gating tier 1: informational warning at crew assignment

- M10 — Layered gating tier 2: warning with override reason at quote acceptance

- M11 — Layered gating tier 3: blocking gate at event_start with override-reason capture

- M12 — "Who can do X" query interface for Ranganai + certification roster dashboard + post-deploy verification

# Phase 7b — Onboarding & Self-service

Second sub-phase. Adds onboarding workflow plus the crew self-service portal.

| Field | Detail |
| --- | --- |
| What it includes | Fixed onboarding curriculum (same sequence for every new hire). Probation period tracking (90 days, formal milestone). Mentor pairing (explicit field on new-hire record). Crew self-service portal — read-only own records, view own upcoming expiries, view own training history. |
| Scope of portal access | Permanent + regular crew only (~10–15 users), not all freelancers ever booked. Per Robin's clarification (Q1A) on 20 May 2026. |
| What it excludes | External course booking (7c). KB articles (7d). |
| Dependencies | Phase 7a complete and stable in production. Crew user records need to exist or be created during this sub-phase. |
| Value at completion | New hires move through a defined curriculum. Probation milestones surface automatically. Crew members can self-check their certification status on phone (mobile-first UX). |
| Milestones (est.) | 4–5 |
| Build time (est.) | ~1–1.5 weeks |

# Phase 7c — External Training & Booking

Third sub-phase. Vendor records, course catalog, booking workflow, formal approval (mirrors Phase 6 quote approval pattern).

| Field | Detail |
| --- | --- |
| What it includes | Vendor records (training providers — MA Lighting, AVIXA, NSSA, etc.). Course catalog with prices, dates, locations. Booking records linking attendee + course + dates + cost. Formal approval workflow (Kudzi submits, Robin/Munashe approve, same pattern as Phase 6 quote approval queue). Post-completion certification linkage — when course is complete, attendee's certification record is created/updated from the booking. |
| What it excludes | Phase 6 cost integration is NOT included — per Robin's A5=A decision, training costs stay in a separate Phase 7 expense model and do not flow to event P&L. This can be revisited in Phase 8+ if value emerges. |
| Dependencies | Phase 7a complete (certification model needed for post-completion linkage). |
| Value at completion | Office staff and Robin/Munashe approve external training expenditure formally. Booking history per crew member visible. Vendor relationships tracked. |
| Milestones (est.) | 3–4 |
| Build time (est.) | ~1 week |

# Phase 7d — Custom Knowledge Base

Fourth and final sub-phase. SOP repository, articles, search, permissions, versioning. Robin chose custom build over Odoo's built-in module (decision F1=A, then again at clarification on 20 May 2026).

| Field | Detail |
| --- | --- |
| What it includes | Article model with rich text content. Category hierarchy (collapsible tree). Tagging system. Search (full-text). Permissions — Robin/Munashe-only authoring (per F2=A); read access broader (likely all training-system users). Version history (drafts vs published). Attachment support (images, PDFs in SOPs). |
| What it excludes | Comments/discussion on articles (could be added later if needed). External (client-facing) KB — internal only. |
| Dependencies | Phase 7a complete (the cert/competency context informs which SOPs are relevant). |
| Value at completion | Institutional knowledge captured in a searchable structured form. New hires onboard against SOPs. "How we do things at Neon" is documented, not just in Robin's head. |
| Milestones (est.) | 5–7 |
| Build time (est.) | ~3–4 weeks |
| Open question | Custom KB vs Odoo built-in — Robin's choice locked at B (custom) but Tatenda is sending one final confirmation given the substantial time difference (3–4 weeks custom vs 1 week built-in vs hybrid mid-ground). Schema sketch for 7d defers until that confirmation lands. |

# Order of build

Suggested execution order: 7a → 7b → 7c → 7d. Reasoning:

- 7a anchors the certification model that 7b's onboarding, 7c's external bookings, and 7d's permissions all depend on.

- 7b lands second so crew portal exists for crew to see their own records as they're recorded by 7c bookings.

- 7c lands third — by then the crew records and certification model are settled enough for external bookings to feed cleanly into them.

- 7d lands last because (a) it's the largest individual sub-phase and (b) it's the most independent — KB content doesn't depend on certifications being in place, just on the institutional infrastructure being settled.

Each sub-phase ends with a tagged production release and a Robin/Munashe walkthrough — same shape as Phase 6's M12. Decisions about polish or refinement land before the next sub-phase opens.

# Cumulative timeline (estimate)

| Sub-phase | End week | Production state at that point |
| --- | --- | --- |
| 7a complete | Week 3 | Core certifications + competency + event_job gating LIVE. Ranganai records certs. Sales reps see qualification status. Layered gates fire at assign / quote / event-start. |
| 7b complete | Week 4.5 | Onboarding curriculum live for new hires. Probation tracking active. Crew self-service portal live for ~10–15 permanent + regular crew. |
| 7c complete | Week 5.5 | External training bookings + formal approval workflow live. Kudzi books, Robin/Munashe approve. Bookings link to certifications on completion. |
| 7d complete | Week 9–10 | Custom KB live. SOPs accessible. Phase 7 fully complete. |

These are estimates against Phase 6's actual cadence. If 7a runs slower or faster, the rest shifts accordingly. Robin's A6=B preference (quality over speed) means we don't compress — we ship when ready.

# Risks worth flagging upfront

| Risk | Severity | Mitigation |
| --- | --- | --- |
| 7d (custom KB) is large and may pull focus from Phase 8–12 work | Medium | Sending Robin a final KB confirmation note (built-in vs custom vs hybrid). If he reconsiders to hybrid, 7d shrinks to ~2 weeks |
| 7b crew self-service portal requires giving ~10–15 crew Odoo logins, password resets, etc. | Low-Med | Scope is small (~15 users). Pattern proven from Phase 6 (Robin and Kudzi user setup). Could WhatsApp-onboard each user individually |
| Cross-competency model (Robin's A4 note) is novel — no prior phase pattern | Low | Schema sketch designs it explicitly; M6 of 7a builds it; can refactor based on first production use |
| Soft skills tracking (B1=D) includes 10 categories that span very different shapes | Low | Schema design covers each as its own certification type within a 'Soft Skills' category. Free-text notes available for nuance |
| External training cost (A5=A) staying separate may feel disconnected from event P&L during walkthrough | Low | Robin explicitly chose this. Can revisit in Phase 8+. Defer to live feedback |

# Master plan implications

The master plan stays at 12 phases. Sub-phase staging is internal.

Revised position:

- Phase 6 — Finance Module (DONE, live 19 May 2026)

- Phase 7 — Training System (this proposal: 7a / 7b / 7c / 7d, ~8–10 weeks)

- Phase 8 — Reports & Analytics (next after Phase 7)

- Phase 9 — WhatsApp Integration

- Phase 10 — Production Hardening

- Phase 11 — Cutover & Training (legacy PHP retirement + parallel run)

- Phase 12 — UI/UX Polish

After 7a ships, project_phase7_status.md is created as a parallel tracking document to project_phase6_status.md. Memory entries reflect the active sub-phase.

# Next steps

- Approve this staging proposal (or revise) — Tatenda

- Send Robin the custom-KB confirmation note (separate WhatsApp / chat)

- Review Phase 7a Schema Sketch (separate document, delivered in parallel)

- Once schema sketch is locked, begin Phase 7a Milestone 1: certification.category + certification.type models